## Task Scope
Task Name | Task Area | Scope
task-1-datacollection | Image Dataset Source | ODE
task-1-datacollection | Image Type (MRO, Rover etc.) | Only MRO Image (HiRISE)
task-1-datacollection | Number of Images | Not a concern
task-1-datacollection | Number of Anomalies | Upto 10
task-2-data-preprocessing | Image Processing | Chunk size of 227x227
task-2-data-preprocessing | Image Labeling | Using Unsupervised or Self - Supervised Learning
task-3-research-models | Model Selection | Not more than 3
task-4-model-building | Number of Models | Transfer Learning
task-4-model-building | Number of Cycles for Training
task-5-model-deployment | Frontend and Backend requirements | Streamlit will be used to save effort
task-5-model-deployment | Model Size
task-5-model-deployment | Deployment Platform | Heroku

## Task Estimation
Task Name | Task Size (S, M, L, XL) | Task Effort (in Hrs)
Pre-requisite
Data Discovery | S
Data Understanding | S
Data Feasibility Study | S
Domain Study and Understanding | M
task-1-datacollection | L | 100
task-2-data-preprocessing | L | 120
task-3-research-models | M | 80
task-4-model-building | M | 100
task-5-model-deployment | M | 80

## Task Management
Task/Sub-Task Name | Task/Sub-Task Description | Task Leader | Duration/End Date | Task/Sub-Task Status | Task/Sub-Task Summary | Sub-Task Team Member
task-1-datacollection |  | Adish Golechha | Week1/Dec 25th | Done
Identify Data Source | Zenodo and ODE |  |  | Done |  | Girish, Kanak, Venkata, Adish, Harshal, Hardik, Shreya
Gather Image Dataset | Download manually or Using Automated scraper provided by Adish |  |  | Done |  | Girish, Kanak, Venkata, Adish, Harshal, Shreya, Larry
Identify List of Anomaly | Need to categorize and reason for that Anomaly |  |  | Done |  | Tanisha, Harshal, Hardik, Avinash, Girish
Image type selection | MRO, Rover etc. |  |  | Done | MRO Images will be used for now | Avinash, Harshal, Tanisha
Finalize Image to be used | From ODE (Requires processing - Chunks, Labelling and Annotation) From Zenodo (Has processed data - Chunks and Labelled but Annotation need to be done) |  |  | Done | Zenodo dataset will be used but need to confirm Clustering algorithm for segmentation | Avinash, Harshal, Hardik, Tanisha
Upload Images to GitHub/Google Drive | Google Drive will be preferred as it allows upload of large size/number of images |  |  | Done |  | Larry, Girish, Harshal, Shreya, Tanisha, Hardik
Acceptance Criteria
task-2-data-preprocessing |  | Avinash Das | Week2/Jan 1st | Done
Review and Execute ODE REST API | Leveraging previous work done by Omdena Team |  |  | Done |  | Hardik, Harshal, Tanisha, Girish, Shreya, Vamsi
Image Transformation | Chunks, Labelling, Annotation,Sharpening, Thresholding,Contour Detection |  |  | Done |  | Tanisha, Harshal, Hardik, Avinash, Shreya, Vamsi, Larry
Image Segmentation | Semantic vs Instance Segmentation |  |  | Done |  | Tanisha, Harshal
Data Augmentation | Flipping, Rotation, Cropping etc. of Image
Annotation Format | COCO vs YOLO vs JASON |  |  | Done |  | Avinash, Hardik, Vamsi, Harshal, Kanak, Adish, Larry
Acceptance Criteria
task-3-research-models |  | Shreya Chawla | Week2/Jan 1st | Done
Identify suitable model |  |  |  | Done |  | Shreya, Tanisha, Harshal
Justify usage of model |  |  |  | Done |  | Shreya, Tanisha, Rik, Hardik
Finalize model to be used |  |  |  | Done |  | Shreya, Tanisha, Girish, Vamsi
Acceptance Criteria
task-4-model-building |  | Girish Sahu | Week3/Jan 8th | Done
Tensorflow/Keras vs Pytorch | Keras API for TensorFlow 2.0 will be used |  |  | Done |  | Girish, Shreya, Tanisha
Feature Engineering | Feature Extraction and Feature Selection |  |  | Done
Transfer Learning | U-Net vs YOLO vs Mask R-CNN |  |  | Done |  | Shreya, Tanisha, Girish, Hardik
Google Colab Pro Account | Need account with GPU access |  |  | Done |  | Toshita, Girish
Model Training and Validation |  |  |  | Done |  | Tanisha, Harshal, Hardik
Model Evaluation |  |  |  | Done |  | Tanisha, Harshal, Hardik
Model Testing |  |  |  | Done
Model Optimization |  |  |  | Done
Acceptance Criteria
task-5-model-deployment |  | Vamsi Chittoor | Week4/Jan 15th | Done
Streamlit vs Flask vs Django | Streamlit will be used |  |  | Done |  | Vamsi, Shekhar, Toshita
Deployment readiness |  |  |  | Done |  | Vamsi, Venkata, Hardik
Model Deployment |  |  |  | Done
System Testing |  |  |  | Done
Acceptance Criteria
Model Monitoring

## Team Capacity
Team Member | Number of Hours available per week (Including weekend) | Task Area Interest/Knowledge | Team Role
Adish Golechha |  |  | Task Leader
Avinash Das |  |  | Task Leader
Girish Sahu | 10 |  | Task Leader
Harshal Hirpara
Jenil Malkan | 12 | Model Building, Model deployment and also can contribute in other task as per my knowledge
Kanak Tekwani | 10
Larry Pallozzi | 2021-10-15 | Willing to help/learn with all remaining tasks, though have limited experience/knowledge
Rik Dutta
Shreya Chawla |  |  | Task Leader
Sunveg Nalwar
Shekhar Gaikwad
Tanisha Banik
Toshita Sharma |  |  | Chapter Leader
Vamsi Chittoor | 10 | Research models / Model Deployment(interest areas) | Task Leader
Venkata Narayana Bommanabonia
Hardik Tejani | 10 | Model Deployment (Area of interest) and willing to help in any task

## Model Selection
Model Name | Model Type | Model Purpose | Model Framework | Model Backbone
DBSCAN | Unsupervised | Clustering/Segmentation | sci-kit learn
K-Means | Unsupervised | Clustering/Segmentation | sci-kit learn
SSD (Single Shot Multibox Detector) | Supervised | Classification |  | ResNet
Mask R-CNN | Supervised | Classification |  | ResNet
U-Net | Supervised | Classification
Ano-GAN | Unsupervised | Segmentation
YOLOR | Supervised | Classification
YOLOv4 | Supervised | Classification |  | DarkNet
Long-Tail | Self-Supervised | Instance Segmentation | PyTorch
Dense Contrastive Learning | Self-Supervised
Parallel Detection-and-Segmentation Learning | Self-Supervised | Weakly Supervised Instance Segmentation
Equivariant Attention Mechanism | Self-Supervised | Weakly Supervised Instance Segmentation
CAM (Class Activation Mapping)